## Slide 1: 2017 CENTRAL VALLEY FLOOD PROTECTION PLAN (CVFPP) UPDATE & SUPPLEMENTAL PROGRAMMATIC EIR (SPEIR) August 26, 2016
2017 CVFPP UPDATE
Notes: Pointer – visible
SBFCA there for questions

## Slide 2: 2017 CVFPP UPDATE & SPEIR
2017 CVFPP Update
  Update teams (review, coordination and integration) continue to meet bi-weekly
  2017 CVFPP Update Administrative Draft to be released in mid-September. Update teams will be reviewing the Admin Draft.
  Continuing to plan the Update public hearings in coordination with the SPEIR public meetings.
Supplemental Programmatic Environmental Impact Report (SPEIR)
  Ongoing bi-weekly coordination meetings with DWR SPEIR team
  Tribal coordination – DWR tribal liaison has joined the tribal consultation efforts. SPEIR team mailed letters in response to tribes requesting coordination. SPEIR team awaiting tribal response to schedule meetings.
  Ongoing coordination regarding Update public hearings & SPEIR public meetings regarding locations and venues.
Notes: And an analyst to assisst

## Slide 3: TENTATIVE SCHEDULE (1/2)
Board and DWR staff have developed the following tentative schedule:
2017 CVFPP Update Milestones:
  Administrative Draft (mid-September 2016)
  Stakeholder Draft (October 2016)
  Public Draft released and presented at December 16, 2016 Board meeting
  Public Hearings conducted (January – mid February 2017, close comments)
  Consider and address comments on 2017 CVFPP Update (March - April 2017)*
  Finish any revisions to Final Draft of the Plan and draft the Adoption Resolution (May – early June 2017)*
  DWR present changes to Public Draft and Board staff presents and recommends adoption of the 2017 CVFPP Update Package at the June 2017 Board meeting, including:
    Board Resolution to adopt the Final Draft of 2017 CVFPP Update, SPEIR Findings, and other documents to be adopted

## Slide 4: TENTATIVE SCHEDULE (2/2)
2017 CVFPP SPEIR Milestones:
  Tribal coordination - ongoing, meetings TBD
  SPEIR Public Draft release and NOC at December 16, 2016 Board meeting
  45-day minimum public review period
  Public Meetings during public review period (January 2017)
  Final SPEIR Certification (May 2017)
  Prepare Board Findings for Adoption (May – early June 2017)
Board Meeting Items:
  Regular Board briefings from DWR and Board staff on relevant topics
  Hold special public hearings (as discussed)
  Discuss and present 2017 CVFPP Update comments and any potential changes
  Release the Public Draft and present Final Draft of 2017 CVFPP Update at regularly scheduled Board meetings in December 2016 and June 2017, respectively

## Slide 5: QUESTIONS
Presented by: Ruth Darling, Senior Environmental Scientist