## Slide 1: CW Budget Process
Beth Salyers
Civil Works Project Management Branch Chief
Sacramento District, USACE
May 10, 2019
Notes: Pictures:
SPN - South San Francisco Shoreline
SPK – Folsom Dam - Release
SPA – Alamogordo Phase VIII
SPL – Port of Los Angeles

## Slide 2
Agenda
Introduction
Civil Works Project Cycle
Program and Funding Timetable
Budget Cycle
WorkPlan Development
Budget Requirements
Non-Federal Sponsor Input

## Slide 3: CW Project Cycle
O&M phase
Product = O&M Manuals, Inspection Reports
Agreement = none. Generally undertaken by sponsor except for Federal NAV and FDR projects
O&M Funding
Pre Construction Engineering and Design phase
Product = Detailed Design Report
Agreement= Design
Investigations Funding
Feasibility phase
Product = Feasibility Report
Agreement = Feasibility Cost Sharing Agreement (FCSA)
Investigations Funding
Construction phase
Product is built
Agreement =Project Partnering Agreement (PPA)
Construction Funding
DESIGN
CONSTRUCTION
PROJECT
INITIATION
OPERATIONS
AND
MAINTENANCE
PLANNING
PROJECT INITIATED BY LOCAL SPONSOR
Study Authorization
Letter of Intent
Feasibility Report Completion
Chief’s Report
Construction Authorization

## Slide 4: Program and Funding Timetable
DEVELOP
FEB INITIAL OMB CEILING AND COST ESTIMATE UPDATE
MAR PROGRAM AND BUDGET ENGINEER CIRCULAR
APR PROGRAM SUBMISSION
JUN OMB CEILING REVISION
JUL HEADQUARTERS PROGRAM REVIEW
DEFEND
AUG ASA(CW) REVIEW
SEP OMB SUBMISSION AND OMB HEARINGS
NOV OMB PASSBACK
FEB PRESIDENT'S BUDGET
MAR ASSISTANT SECRETARY OF THE ARMY (CIVIL WORKS) AND CORPS APPROPRIATIONS HEARINGS
JUN HOUSE APPROPRIATIONS BILL
JUL SENATE APPROPRIATIONS BILL
AUG CONFERENCE
EXECUTE
SEP APPROPRIATIONS ACT
OCT APPORTIONMENT, WORK ALLOWANCES, AND IMPLEMENTATION PLANS
DEC-JAN SCHEDULES OF OBLIGATIONS AND EXPENDITURES (2101)
EOY REVIEW PROGRESS AND REPROGRAM FUNDS AS NEEDED
FY19 |  |  |  |  |  |  |  |  | FY20 |  |  |  |  |  |  |  |  |  |  |  | FY21 |  |  |  |  |  |  |  |  |  |  | 
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
FY19 PROGRAM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
EXECUTE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
FY20 PROGRAM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
DEFEND |  |  |  |  |  |  |  |  | EXECUTE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
FY21 PROGRAM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
DEVELOP |  |  |  |  |  |  | DEFEND |  |  |  |  |  |  |  |  |  |  |  |  |  | EXECUTE |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  | FY22 PROGRAM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  | DEVELOP |  |  |  |  |  |  | DEFEND |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | FY23 PROGRAM |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DEVELOP |  |  |  |  |  |  | DEFEND | 

## Slide 5
2) HQ Provides Program Guidance ( Mar )
4) HQ Review & Approval
( May -Jun )
5) Program Presented
to Secretary of the Army
(Jul - Aug )
7) OMB Passback
( Nov-Dec )
6) Program Submitted to OMB ( Sep )
8) President’s Budget
to Congress ( Feb )
3) Field Offices Develop
Program Requirements
( Apr )
10) Appropriations Bills
( Jul - Sep )
9) Congressional Hearings ( Mar - Apr )
11) President Signs Appropriations Bill
( Sep - Oct )
1) OMB Provides Budget
Guidance (Jan)
12) Funding Allocations to Field Offices
( Oct - Dec )
13) Districts Execute current FY Program
( Oct - Sep )
Develop the Program
Defend the Program
Execute the Program
The Program Cycle

## Slide 6: CW Workplan Development
10) DRAFT Appropriations Bills
( Jul - Sep )
11a) Continuing Resolution
( Sep - ??? )
13a) Full year funding Bill
14a) Workplan Process & funding allocation decisions
15a) Workplan Published
16a) Funding arrives
12a) Pro-rated funding allocations for CR Period

## Slide 7: PERFORMANCE BASED BUDGETING
President’s Budget switched to Performance-Based Budgeting in compliance with the Government Performance and Results Act of 1993 (GPRA) to maximize the use of the federal dollars
Performance measures are used to:
  Rank competing investments from each business line
  Justify funding allocations for continuing and new projects
Goal: Fund highest priority work at an efficient rate

## Slide 8: Budget REQUIREMENTS
  Investigations:
  SMART 3x3 compliant – with Compliance memo or exemption
  New Study after WRRDA 2014
  Federal Interest
  Non-Federal sponsor and local support
  Compliance with NEPA and other Environmental regulations
  Completed and approved Sec 216 Review of Completed Projects
  Construction:
  Authorized for Construction
  Approved Chief’s report, major rehabilitation report or Dam Safety Modification Report
  High economic return and benefit-to-cost (BCR) ratio of 2.5 to 1 or higher calculated at 7% discount rate
  New start and new investment decisions - High performance measures, a Decision Document approval prior to budget submission and Current economic analysis
Notes: Investigation:
Eligibility and Ranking:
SMART compliant
Compliance Memo, Exemption, or a new Feasibility study after WRRDA 2014
Have Federal Corps interest
Matter of urgency for implementation of the problem solution
Non-Federal sponsor and local support (Letter of Intent within 5 months of MSC budget submission date – net 1 Dec 2018)
In compliance with NEPA and other environmental regulations
Standard funding stream: 36 months over 4 FY; $200K/$600K/$600K/$100K
Construction:
Eligibility:
Authorized for Construction
Approved Chief’s report, major rehabilitation report or Dam Safety modification report
Ongoing projects funded based on their economic return and have a benefit-to-cost (BCR) ration of 2.5 to 1 or higher calculated at 7% discount rate
Continuing PED and Construction need economic update no older than 5 years from budget submission (1 May 2014 for a FY21 Budget request.
New start and new investment decisions
  High performance measures
  Decision Document approval prior to budget submission
  Current economic analysis (no older than 3 years from submission (1 May 2016 for a FY21 budget request)

## Slide 9: NF Partner Input
Letters of Intent
Project Delivery Team Members
  LERRDS
  Optimal Funding Stream (Fed and NF)
  Program Execution
Communication
  Consistent
  Transparent

## Slide 10: QUESTIONS